## Start here
Home building budget template
Free from Groundbase: getgroundbase.com
1. Budget tab: replace the example line items and amounts with your builder's budget. Add rows inside a section and the subtotal picks them up.
2. Allowances tab: enter each allowance from your contract and the running total of your picks. Type Yes under Decided once every pick is final.
3. Budget tab, change orders: add each change with its amount. Set the status to Approved and it counts toward the projected total.
4. Draws tab: as each draw is paid, split it between the bank and your cash.
5. Funding tab: enter your loan, closing costs, down payment, sale proceeds and cash to see what is left over, or short.
Shaded cells are inputs. Everything else is calculated.
Over / under reads in words: "$2,600 over" or "$430 under".
When the build is moving, Groundbase does all of this without formulas, and adds loan interest, your DTI and the finished mortgage payment.

## Budget
Home building budget
Example numbers from a sample $712,000 build. Replace the shaded cells with yours; every total updates.
Line item | Budget | Actual | Over / under | Notes
Land and site work
Survey and soil test | 4000 | 4000
Clearing and excavation | 24000 | 24000
Driveway | 26000 | 26000
Septic and water | 20000
Land and site work subtotal
Soft costs
Plans and engineering | 14000 | 14000
Permits and impact fees | 9500 | 9500
Builder's risk insurance | 3500 | 3500
Soft costs subtotal
Structure
Foundation | 58000 | 58000
Framing | 96000 | 96000
Roofing | 28000 | 28000
Windows and exterior doors | 32000
Siding | 24000
Structure subtotal
Systems
Plumbing | 34000 | 34000
Electrical | 32000 | 32000
HVAC | 38000 | 38000
Systems subtotal
Interior
Insulation | 12000
Drywall | 30000
Trim and millwork | 26000
Paint | 22000
Final clean and punch list | 6500
Interior subtotal
Allowances
All allowances (detail on the Allowances tab) |  |  |  | Picks and over/under live on the Allowances tab
Contingency
Contingency (about 10% of construction) | 66000 |  |  | For the surprises you will not avoid
Change orders
Change order | Amount | Status |  | Notes
Fireplace | 7000 | Approved
Backyard grading | 5000 | Approved
Siding upgrade | 3000 | Approved
Front door | 2500 | Approved
Conduit line | 300 | Approved
Paint upgrade | 15000 | Pending |  | Not counted until you approve it
Build budget
Approved change orders
Allowance overage, counted
Projected total
Against the budget

## Allowances
Allowances and selections
Overages count right away. Savings count only once every pick under the allowance is decided, so a half-picked allowance never looks like money saved.
Allowance | Allowance amount | Selections total | Decided? | Over / under | Counted toward budget
Kitchen | 30000 | 29570 | Yes
Garage door | 5000 | 6625 | No
Bath vanities | 4000 | 6600 | Yes
Bath fixtures and faucets | 4000 | 4238 | Yes
Lighting and fans | 1500 | 493 | No
Exterior doors and hardware | 10000 |  | No
Interior doors and hardware | 10000 |  | No
Flooring material and labor | 27000 | 35483 | Yes
Stairs and railings | 15000 | 13500 | Yes
Total
Decided? Type Yes once every pick under that allowance is final.

## Draws
Draw schedule
Each builder draw, and how it was paid: by the bank (construction loan) or by your cash.
Draw | Amount | Paid by bank | Paid by cash | Not covered yet | Status
Builder down payment | 10000 | 0 | 10000 |  | Paid
Driveway and mason | 110000 | 0 | 110000 |  | Paid
Framing, roofing, siding, windows | 252000 | 102000 | 150000 |  | Paid
Septic and water | 20000 | 0 | 0 |  | In progress
HVAC, electrical, plumbing | 110000 | 110000 | 0 |  | Paid
Insulation, drywall, paint | 80000 | 0 | 0 |  | Not started
Millwork, countertops, flooring | 85000 | 0 | 40000 |  | Not started
Grading | 20000 | 0 | 0 |  | Not started
Final payment | 25000 | 0 | 0 |  | Not started
Total

## Funding
Paying for the build
Every source of money against the projected cost. Shaded cells are yours to change.
| Amount | Notes
Projected total |  | From the Budget tab
Extras outside the contract | 12000 | Appliances, furniture, the move
Construction loan | 400000 | The full loan amount
Less closing costs | 10000 | Often withheld from the first bank draw
Down payment | 10000 | Paid to the builder at signing
Sale proceeds | 310000 | Net from selling your current home
Your cash | 109400 | Savings and other cash
Money available
Money needed
Left over (or short)
5% reserve |  | 5% of the build budget, kept for surprises
To spare after the reserve